## Weekly Hours Log
RA-MemeStocks Project — Research Assistant Weekly Hours Log
RA: Rajvardhan Patil ¦ Project: Impact of Reddit Server Outages on Meme Stock Returns ¦ Start Date: February 2, 2026 ¦ Max 10 hrs/week
Week | Date Range | Phase / Category | Task Description | Hours | Week Total
W01 | Feb 2 – Feb 8, 2026 | Project Setup & Literature Review | Reviewed project scope and research question with supervisor | 1.5 | 9.5
|  |  | Literature review: meme stock mechanics and Reddit WallStreetBets dynamics | 3
|  |  | Read key reference paper: 'Squeezing Shorts Through Social Media Platforms' | 2
|  |  | Set up local project repository and folder structure | 1
|  |  | Identified data sources: WRDS TAQ for GME/AMC, CRSP for SPY, Ken French library | 2
W02 | Feb 9 – Feb 15, 2026 | Data Collection & Initial Preprocessing | Downloaded raw minute-level TAQ price data for GME and AMC (Nov 2020 – Apr 2021) | 2.5 | 9.5
|  |  | Downloaded SPY minute-level prices from WRDS | 1
|  |  | Downloaded Fama-French daily and monthly factor data from Ken French data library | 1
|  |  | Constructed minute-level Fama-French factors from ETF prices (SPY, VUG, VTV, IWM, VV, MTUM) | 2.5
|  |  | Built ff_factor_minute_construction.ipynb to document factor construction | 1.5
|  |  | Initial commit: pushed all raw data files and ETF price CSVs to repository | 1
W03 | Feb 16 – Feb 22, 2026 | Excess Return Calculation & CAPM Event Study | Built exceed_return_calculation.ipynb to compute GME/AMC/SPY excess returns | 1.5 | 8.5
|  |  | Generated cleaned minute-level excess return CSVs for GME, AMC, and SPY | 1
|  |  | Verified data quality: de-duplication, sorting, and missing-value audit | 1
|  |  | Built meme_stock_outage_analysis.ipynb: full CAPM event study (4 outage windows) | 2.5
|  |  | Implemented CAPM estimation window (120-day, 2-day lag) in Python | 1
|  |  | Implemented Fama-French 4-factor model (FF4) in meme_stock_outage_ff4.ipynb | 1.5
W04 | Feb 23 – Mar 1, 2026 | Methodology Refinement & Model Validation | Reviewed CAPM and FF4 estimation results; validated alpha/beta estimates | 2 | 7.5
|  |  | Cross-checked CAR figures against manual calculations for 2 outage events | 2
|  |  | Discussed methodology with supervisor: CAR normalisation and pre-period handling | 1.5
|  |  | Refined event study design: added 1-hour pre-period to event windows | 1
|  |  | Planned multi-frequency robustness analysis (5-min and 10-min bars) | 1
W05 | Mar 2 – Mar 8, 2026 | Multi-Frequency Data & Analysis | Constructed 5-min and 10-min aggregated return series for GME and AMC | 2 | 9.5
|  |  | Built multi-model excess return CSVs (CAPM, FF3, FF4) at 1/5/10-min frequencies | 2.5
|  |  | Built meme_stock_outage_multi_freq.ipynb: FF4 vs CAPM at 5-min and 10-min bars | 2
|  |  | Built excess_return_multi_model.ipynb: side-by-side multi-model comparison | 1.5
|  |  | Generated initial multi-frequency output figures for all 4 outage events (GME & AMC) | 1.5
W06 | Mar 9 – Mar 15, 2026 | Recovery Analysis & Figure Refinement | Designed post-outage recovery analysis methodology (+30m, +1h, +2h horizons) | 1.5 | 7.5
|  |  | Implemented calculate_recovery_car() in event_study.py with Patell t-stats at each horizon | 2
|  |  | Added after-hours SPY fallback logic to FF4 model for recovery windows | 1.5
|  |  | Refined all event-window and recovery figures in visualizations.py | 1.5
|  |  | Updated FF4 and multi-freq notebooks to incorporate recovery methodology | 1
W07 | Mar 16 – Mar 22, 2026 | Results Review & Documentation | Reviewed all CAR and recovery results with supervisor; noted discrepancies | 2 | 7
|  |  | Audited multi-frequency data: discovered duration calculation bug in multi-freq CSVs | 2
|  |  | Planned fix for multi-freq time-duration issue and data re-construction | 1.5
|  |  | Documented methodology notes and edge cases (after-hours fallback, Outage 4 gaps) | 1.5
W08 | Mar 23 – Mar 29, 2026 | Bug Fixes, Recovery Results & Figure Updates | Fixed time-duration calculation bug in multi-freq data pipeline; regenerated all multi-freq CSVs | 2 | 10
|  |  | Regenerated all multi-freq figures (5-min and 10-min, GME and AMC, all 4 events) | 1.5
|  |  | Expanded event_study.py with full recovery analysis (150+ lines) and run_recovery_analysis() | 2
|  |  | Expanded FF4 notebook with complete recovery event study and FF4 recovery CSV | 1.5
|  |  | Added realized volatility figure and cross-frequency comparison plots | 1.5
|  |  | Updated config.py and visualizations.py to support recovery analysis outputs | 1.5
W09 | Mar 30 – Apr 5, 2026 | Output Table Generation | Built generate_tables.py: full LaTeX/CSV table generation pipeline (417 lines) | 2.5 | 7.5
|  |  | Generated Table 1 (CAPM) and Table 2 (FF4) result tables with t-stats and p-values | 1
|  |  | Generated Tables 3–4: multi-frequency FF4 vs CAPM comparison tables | 1
|  |  | Generated Tables 5–7: post-outage recovery tables at all frequencies | 1.5
|  |  | Generated Table 8: CAPM pre-ban vs post-ban summary table | 0.5
|  |  | Verified all LaTeX table formatting and CSV outputs | 1
W10 | Apr 6 – Apr 12, 2026 | Statistical Completeness, README & Deliverables | Identified missing t-statistics in FF4 and multi-frequency tables | 0.5 | 6.5
|  |  | Built compute_tstats.py: re-estimates FF4/multi-freq sigma and appends t-stats to CSVs | 2
|  |  | Updated generate_tables.py: added t-stat/p-value columns to Tables 2, 3, 4, 8 | 1.5
|  |  | Added table description docstrings and generated table_descriptions.csv/.tex | 0.5
|  |  | Wrote project README.md with full methodology, data sources, and reproduction guide | 1.5
|  |  | Drafted progress email to supervisor (Matthew) with all file paths and change summary | 0.5
GRAND TOTAL |  |  |  |  | 83

## Weekly Summary
Weekly Hours Summary
Week | Date Range | Phase | Hours | Status
W01 | Feb 2 – Feb 8, 2026 | Project Setup & Literature Review | 9.5 | ✓ Within limit
W02 | Feb 9 – Feb 15, 2026 | Data Collection & Initial Preprocessing | 9.5 | ✓ Within limit
W03 | Feb 16 – Feb 22, 2026 | Excess Return Calculation & CAPM Event Study | 8.5 | ✓ Within limit
W04 | Feb 23 – Mar 1, 2026 | Methodology Refinement & Model Validation | 7.5 | ✓ Within limit
W05 | Mar 2 – Mar 8, 2026 | Multi-Frequency Data & Analysis | 9.5 | ✓ Within limit
W06 | Mar 9 – Mar 15, 2026 | Recovery Analysis & Figure Refinement | 7.5 | ✓ Within limit
W07 | Mar 16 – Mar 22, 2026 | Results Review & Documentation | 7 | ✓ Within limit
W08 | Mar 23 – Mar 29, 2026 | Bug Fixes, Recovery Results & Figure Updates | 10 | ✓ Within limit
W09 | Mar 30 – Apr 5, 2026 | Output Table Generation | 7.5 | ✓ Within limit
W10 | Apr 6 – Apr 12, 2026 | Statistical Completeness, README & Deliverables | 6.5 | ✓ Within limit
TOTAL HOURS |  |  | 83